## Client priority
S. No. | Page | Description | Priority | Dev Status | Tentative date | Attachment | Developer | Dev. comment | Client Comments
1 | Received Payment | 1- House account - Show emplyoe who is receiving the payment. | 1 | Done |  |  |  | Users dropdown added in receive-payment popup: https://prnt.sc/EUfwQ1VRsxzE
2 | Customer > Order History | 1- House account - Show Order history in customer | 1 | Done |  |  |  | added a new tab https://prnt.sc/vmWUuHZHTyRb
3 | Customer > House Account | 1- House account - Show Remaining balance of customer after payment settle | 1 | Done |  |  |  | Please check https://prnt.sc/21vPQnZDKr6s
4 | Received Payment | 1- House account - Under Receive Payment, show all customers in listing which have house account | 1 | Done |  |  |  | https://prnt.sc/-yaskXHXCR6K
5 | Received Payment | 1- House account - User can receive payment even without generating statement | 1 | Done
6 | Customer > Order History | 1- House account - Show Ticket/order number for which order is created with house account under Customer | 1 | Done |  |  |  | https://prnt.sc/CbjoNYtw8tcG
7 | Customer > General | 1.1 - Customer - If there is no phone number in general, then show the phone number from billing under customer > general | 1 | Done
8 | Received Payment | 1- House account - Payment receive - user can settle single amount in multiple invoices manually | 1 | Done |  |  |  | https://prnt.sc/usMYlpPlqQMr
9 | Statement | 1- House account - Payment Settle - Show all house account invoice, then user can select the invoice and receive payment | 1 | Done
10 | Order Entry | 1- Order > need Save order functionality and after saving the order it will be displayed under Tickets > Filed | 1 | Done
11 | Received Payment | 1- House account - Need to generate receipt, joseph will share the receipt format by Monday | 1 | Done
12 | Received Payment | 1- House account - User should be able to print statement for each customer | 1 | In-progress |  |  |  | It is implemented on the development server and we are testing on it with different scenarios
13 | Frontend | 1- website, it is very slow and not loading, it has to be added to priority loading speed | 1 | In-progress |  |  |  | When uplaoding the changes, so we clearing cache regularly
14 | Frontend | 2- Frontend - product search - should be able to search with sku | 2 | Done |  |  |  | Product search will work with sku now, same as in backend
15 | Tickets | 2- Tickets - Ticket Details - Ticket photos - uploaded signature and images should be displayed here | 2 | Done
16 | Order Entry | 2- order entry > Recipient > address search - show canada addresses on top priority, if possible | 2 | Done
17 | Order Entry | 2- Order entry - need to share email confirmation to user - customer will receive the email | 2 | Done
18 | Mercury - customert | 2- Import customers from mercury and there should not be duplicate entries as POS might have existing users from mercury as well | 2 | Done
19 | Order Entry | 2 - Order > Customer search - need to able to search with billing number, all numbers added by user | 2 | Done
20 | Tickets | 2 - Tickets - Filter order which are placed from frontend and new orders should be displayed under New Tab | 2 | Done |  |  |  | New orders will be displayed under the new tab, and they will be confirmed after clicking on confirm button in view section and then will be displayed under confirmed tab
21 | Order Entry > Browse Products | 2 - order entry > Browse products - need an option from when user can see the product description | 2 | Done |  |  |  | on click of the title user will be redirected to description page
22 | Order Entry > Browse Products | 3 - order entry > Browse products - show default category selected as Occasions > Mother's day, upto mother's day | 3 | Done
23 | Order Entry | 3 - order entry > user should be able to add discount for delivery charges | 3 | Done
24 | Tickets | 4 - Tickets - The tabs should show the related tickets like Confirmed, Filed | 4 | Done |  |  |  | All tabs will show the related data
25 | Driver | 4 - Driver - after saving the signature, user should be redirected back, do not keep the user on the same page | 4 | Done
26 | Driver | 4 - Driver - after saving the order as Delivered, count is not updating | 4 | Done
27 | Driver | 4 - Driver - should be able to only see delivery information and not other menus | 4 | Done
28 | Driver | 4 - Driver - Show date filter as well and by-default show Today's date, should be able to select back date as well and data | 4 | Done
29 | Driver | 4 - Driver - Show by-default option as All and listing should show data for all drivers | 4 | Done
30 | Order Entry | 5 - order entry > Recipient - First name should be searchable and editable in field itself and not the in the dropdown | 5 | Done
31 | Driver | 5 - Routing Progress - show order details as well when user click on order count | 5 | Done
32 | Order Entry | 6 - Need to send the email confirmation, when the order has been delivered | 6 | Done
33 | Product | 6- Product > Additional Information - need an option to decrease/ increase font size | 6 | Done
34 | Coupons | 6 - Coupons - Status should be functional for frontend as well | 6 | Done
35 | Order entry | 6 - Order Entry > Browse Product - when user search with sku, then all variants are incorrectly appearing in the seach list | 6 | Done
36 | Frontend > My account | 7- Frontend > My account > orders - view order - date of delivery is wrong - check description | 7 | Done | 2024-04-19 | https://prnt.sc/ctSAPXlz-W2J | Sayad
37 | Frontend > My account | 7- Frontend > My account > orders - view order - need to add Thumbnail image of product | 7 | Done | 2024-04-19 | https://prnt.sc/AJch5J2woKn4 | Sayad
38 | Frontend | Frontend > order view, should look like backend tickets with status bar and not the notes | 7 | Done | 2024-04-19 |  | Sayad
39 | Frontend > thankyou | 7- Frontend > Thank you page - product clickable - not redirecting to product | 7 | Done | 2024-04-19 |  | Sayad
40 | Frontend > My Account | 7- Frontend > My Account - My coupons - remove this section for now | 7 | Done | 2024-04-19 |  | Sayad
41 | Order entry | Order entry - not able to enter decimal value, please check screenshot | 7 | Done | 2024-04-19 | https://prnt.sc/yzll9HIyf6iQ | Sanjeev
42 | Order entry | Order entry - card message - centered in the template | 7 | Done | 2024-04-19 |  | Sanjeev
43 | Order entry | Order entry - copy last - should copy everything from the previous ticket, including address, card message, delivery date - copy | 7 | Done | 2024-04-19 | https://prnt.sc/-hOOgvsDxKe7 | Sanjeev
44 | Order entry | Order entry - copy last - create order - tickets - edit order - not showing the details in edit order | 7 | Done | 2024-04-19 |  | Sanjeev
45 | Order entry | Order entry - only show gst/pst or hst, not both at the same time | 7 | Done | 2024-04-19 |  | Sanjeev
46 | Frontend | 7- Frontend > home page > replace choclate to mother's day icon, please check screenshot | 7 | Done | 2024-04-19 | https://prnt.sc/PMsmkuN-i-hY | Sayad
47 | Frontend | Frontend > Text change for Fast Delivery - client will provide the text - both language, please check screenshot | 7 | Done | 2024-04-19 | https://prnt.sc/CqXgeTjeBNeO | Sayad
48 | Products | Products - deleting a product, should be able to create new product or variant with same old sku of deleted product | 7 | Done | 2024-04-19 |  | Sanjeev
49 | Frontend > Product | Frontend > when user hover over the product image - is it possible to show next images | 7 | Done | 2024-04-19 |  | Sayad
50 | Frontend > Recipient Address | 7- Frontend > Recipient Address > Add/ update - Recipitent email - not be mandatory - remove it completely | 8 | Done | 2024-04-23 | https://prnt.sc/qnOvptjZq2nu | Sanjeev
51 | Frontend > Billing Address | 7- Frontend > Billing address - street address, remove monteral, QC, CA from street address, same as working on Recipient addre | 8 | Done | 2024-04-23 | https://prnt.sc/8rKryO6ofW3l | Sayad
52 | Frontend > checkout | 7- Frontend > checkout > recipient dropdown - show complete info in dropdown, complete address city postal code phone number | 8 | Done | 2024-04-23 | https://prnt.sc/WbesvMXnBzPR | Sanjeev
53 | Frontend > checkout | 7- Frontend > checkout > recipient - not filling phone number, location type as saved under recipient address | 8 | Done | 2024-04-23 |  | Sanjeev
54 | Tickets | Tickets - remove recipient email - do not show | 8 | Done | 2024-04-23 | https://prnt.sc/9AU9vRpLvUT3 | Sanjeev
55 | Products | Products > Show record listing from below the search section not from the bottom | 8 | Done | 2024-04-23 | https://prnt.sc/qcVf1JBuTooX | Sanjeev
56 | Products | Products > edit variant - checkbox is incorrectly changing for product listing in background | 8 | Done | 2024-04-23 | https://prnt.sc/5wod0GE43yaS | Sanjeev
57 | front end | when loged in client account the orders tab on left is not there anymore | 8 | Done | 2024-04-23 |  | Sayad |  | 8
58 | Frontend > thankyou | Frontend > thankyou page - Currently we have different view in thankyou page and email, make the text on thankyou page same as that of email | 9 | Done | 2024-04-24 | https://prnt.sc/haGmvxbPAjX2 | Sayad |  | 9
59 | front end | More colors option only on category level | 9 | Done | 2024-04-24 |  | Sanjeev |  | right now you do not see more colors on ctaegory level you see it in product level, shoudl not be in product level onlyin category level show the banner on category level - 9
60 | front end | cleint account recipient when click add you new the province shows manitoba should be empty or quebec, country canada is good | 9 | Done | 2024-04-24 |  | Sanjeev |  | 9
61 | Frontend | Checkout - step 1 - Change heading Pickup/ Delivery Details translate same for french | 9 | Done | 2024-04-24 | https://prnt.sc/-tUgmTAZ51ZF | Sayad |  | 9
62 | Frontend | Need to delete the Billing and Recipient addresses of customer and after deleting, customer should see a message on the Dashboard : "We have made changes to the website, please add Billing and Recipient address" | 9 | Done | 2024-04-24 |  | Sanjeev
63 | Frontend | Rearrange the order : Subtotal, Delivery Charges, GST, PST, Total | 9 | Done | 2024-04-24 |  | Sayad
64 | backend/front end | Card messages in frontend and backend will be displayed as per the selected occasion | 10 | Done | 2024-04-26 |  | Sanjeev | As discussed on call, we will complete the card messages first and thenCard templates will be done with clover and quickbooks tasks | 10
65 | Products | Products > Meta seo, description - only for english, should be for french as well, will it be usefull for seo | 10 | Done on DS | 2024-04-26 |  | Sayad |  | 10
66 | Frontend > checkout | Add recipient details and place order, now check the saved recipient address, observe that phone number is not getting saved | 10 | Done | 2024-04-26 |  | Sanjeev
67 | Frontend > orders | under the client account orders we want to remove the green dot and legend, and add the recipient name in a column to the right of the order number |  | Done | 2024-04-26 |  | Sayad
68 | Frontend | After adding the product to cart, when user enter the login details and then try to login using enter key. | 10 | Done | 2024-04-26 |  | Sayad
|  | the text that we want to change for the user login dash board in english will be the following, if you can add the link to the approriate secitions Welcome to Your Account Dashboard! We're excited to share that we've updated our website to serve you better! From here, you can effortlessly view your recent orders, manage your account settings, and update your password. What's New? • Address Updates Needed: We've upgraded our system, and to ensure that all your details are accurate, we need you to update both your billing and recipient addresses. This quick update will help us make your future shopping experiences smooth and seamless. • Track Your Orders: You can now track the progress of your orders right from your dashboard. Stay updated every step of the way! • Exciting Features Coming Soon: Keep an eye out in the coming weeks as we roll out new features designed to enhance your shopping experience even further. Thank you for keeping your account up to date and for being a valued part of our community! | 10 | Done | 2024-04-26 |  | Sayad |  | Text in french : Bienvenue dans votre tableau de bord de compte ! Nous sommes ravis de partager avec vous que nous avons mis à jour notre site web pour mieux vous servir ! Depuis ici, vous pouvez facilement consulter vos commandes récentes, gérer vos paramètres de compte et mettre à jour votre mot de passe. Quoi de neuf ? • Mise à jour des adresses requise : Nous avons amélioré notre système et pour garantir l'exactitude de vos détails, nous avons besoin que vous mettiez à jour vos adresses de facturation et de livraison. Cette mise à jour rapide nous aidera à rendre vos futures expériences d'achat fluides et sans tracas. • Suivi de vos commandes : Vous pouvez maintenant suivre le progrès de vos commandes directement depuis votre tableau de bord. Restez informé à chaque étape ! • Nouvelles fonctionnalités à venir : Restez à l'affût dans les prochaines semaines, car nous déployons de nouvelles fonctionnalités conçues pour améliorer encore davantage votre expérience d'achat. Merci de tenir votre compte à jour et d'être un membre précieux de notre communauté !
|  | Text chnages : Also under new billing address (FR) and details du compte (FR) change adresse email to adresse courriel Under the details du compte Current password: mot de passe actuel New password; nouveau mot de passe so the email field in both those places in french will be adresse courriel | 10 | Done | 2024-04-26 | https://prnt.sc/dsbe1d54CnUJ https://prnt.sc/eGj-8iJNofYr | Sayad
69 | Frontend > checkout | billing address - show the company address as well in the billing details, in both billing address and checkout > billing address | 10 | Done | 2024-04-26 | https://prnt.sc/gZgk_maJCLOM | Sanjeev
70 | Frontend > checkout | Checkout > Pickup/ Delivery Details > place Next button on right side | 10 | Done | 2024-04-26 |  | Sayad
71 | Frontend > checkout | selecting recipient address from dropdown, change it like the billing address, along with edit | 10 | Done | 2024-04-26 | https://prnt.sc/JYxIuLSC6wp7 | Sanjeev
72 | Frontend > checkout | add button to Add New Recipient Address, same as present on billing address | 10 | Done | 2024-04-26 |  | Sanjeev
73 | frontend | receipient Address type |  | Done |  |  |  | french change accueil to Residence, Office to Bureau, tour a condo/Apartement change to Tour à condo/appartement, we need to add Salon funéraire, (in english)Funeral home
74 | frontend | More colors option only on category level |  | Done |  |  |  | still on product page
75 | frontend | deliver date in french calendar is english |  | Done |  |  |  | need to have french calendar displayed

## Priority task from 14 May
S. No. | Page | Description | Priority | Dev Status | Tentative date | Attachment | Developer | Dev. comment | Client Comments
1 | backend | - Print invoice with card templates | 1 | Done on DS | 2024-05-15 |  | Sanjeev
2 | backend/ frontend | - Implementing card templates | 1 | Done on DS | 2024-05-15 |  | Sayad
3 | front end | put back some categories in the home page put back home sympathy flowers under sympathy, put back the bulf flower section, put back, anniversaries, birthdays, get well, proms, new born under occasion. also remove mothers day |  | Done | 2024-05-16 |  | Sayad | from upwork/ meeting
4 | Tickets | Print - need to be able to print on legal size | 1 | Done on DS | 2024-05-17 |  | Sanjeev
5 | Front end backed | Interactive card templates Card templates should be as per the selected occasion | 1 | Done on DS | 2024-05-17 |  | Sayad
6 | front end | remove 3 banners on the home page, and put back the sympathy banner and custom design banner |  | Done | 2024-05-17 |  | Sanjeev | from upwork/ meeting
7 | backend | funeral category is not showing under Product category or products |  | Done | 2024-05-17 | https://prnt.sc/v-zXkyxrcQO1 | Sanjeev | from upwork/ meeting
8 | front end | Add in mega menu, Customized Specialties for both english and french under Funeral |  | Done | 2024-05-17 | https://prnt.sc/Jb6k3vs7znOf | Sanjeev | from upwork/ meeting
9 | Frontend > checkout | - Clover payment gateway implementation on frontend | 1 | Done on DS | 2024-05-20 |  | Sayad
10 | front end | reduced the font sizes for headings as discussed in meeting, check screenshots for headings |  | Done | 2024-05-20 | https://prnt.sc/GhnuLKT3w87J https://prnt.sc/B-Xux_D9jnt8 https://prnt.sc/mzTCsN3TsYiX | Sanjeev | from upwork/ meeting
11 | front end | add logo for mobile and when user click over it, then redirected the user to home |  | Done | 2024-05-21 |  | Sanjeev | from upwork/ meeting
12 | front end | For Mobile, add the Home menu option in Mega menu, |  | Done | 2024-05-21 |  | Sanjeev | from upwork/ meeting
13 | Quickbooks | - Exporting orders to quickbooks | 1 | Done on DS | 2024-05-23 |  | Sanjeev
14 | Backend | Product > edit variation > Change Type to Select Size Color to Option 1 - show same on frontend Option to Option 2 |  | Done |  | https://prnt.sc/dycGYlFKOVRX https://prnt.sc/-Lbsxx1FGNRl |  |  | for the 4th attribute we would like it to be placed after the colors attribute, the name will be SELECT OPTION(english) and CHOISIR OPTION (french) the attrribute under this will be • With greenery (english)- Avec de la verdure(french) and With greenery and floral accents (english), avec des accents de verdure et de fleurs(french) these are the only 2 right not for this new attribute. We would also need to add to the oiptions attribue; Arranged cut bouquet (english)----Bouquet coupé arrangé (french) and Arranged bouquet in vase(english)---- Bouquet disposé dans un vase(french)
15 | backend | - Delivery email confirmation with checkboxes | 1 | Done |  |  | Sanjeev
16 | backend | - check box should be on the delivery confirmation by default for all web orders coming from frontend. |  | Done
17 | backend | - In Backend, checkboxes as saved or updated by the user under Customer section, same is updated on : - Order Entry > Customer Edit - Product section of Order Entry - Tickets Details |  | Done
18 | backend | - for new accounts created on back end both order confirmation and delivery confirmation should be defaulted as checked as per their client account. |  | Done
19 | backend | - these emails is also dependant on their language. WHICH is still not set on the front end as a client detail |  | Done |  |  |  | check point 21 along with this
20 | Frontend | Frontend > my account - language - no option to choose language | 2 | Done |  | https://prnt.sc/qPxatcaW3n9r | Sayad
21 |  | - Language as selected by the user on frontend under Account Details, will be same displayed on backend |  | Done
22 | front end | Products - need to add 360 degree video with product images as well | 2 | Done on DS |  |  | Sanjeev
23 | backend | in delivery center when product is marked designed its going under not designed column | 2 |  |  |  | Sayad
24 | backend | delivery and order confirmations need to only trigger sending email if checked off | 2 | Done |  |  | Sanjeev
25 | Frontend > logout | Frontend > logout page - do not show wordpress page when user click on logout | 2 | Done |  |  | Sanjeev
26 |  | Show all chosen attributes on cart page |  | Done
27 |  | - More Color banner will be updated on products when user check the checkbox from Product section |  | Done
| backend | sort product varient by size, color, type, option, select option, SKU when editing product SKU can be displayed in a saparate column | 5 |  |  | https://prnt.sc/5ovVqq2yF4kW
28 | Front End | translate the sold out banner on products for the french side' : épuisé | 2
29 | backend | in order entry under billing address when click drop down need to see name and address not only name right now i see all the same names and dont know who i am picking | 2 | Done |  |  | Sayad |  | show complete details like name address and phone in dropdown listing
30 | Backend | Where is the employee name that took the order, need to show employee in tickets listing who is taking the order and for frontend orders show employee as 'Web' | 2 | Done |  |  | Sanjeev
31 | Backend | Backend - show all notes under Product note, Additional info, delivery instructions, product notes | 2 |  |  |  | Sayad
32 | Front End | search does not work in french | 2 | Done
33 | Front End | Apple Pay | 2 |  |  |  | Sanjeev | We need to check the Clover possibility for apple pay | if its easier with clover, we can put it with clover
34 | Front End | The search box on mobile does not appear properly when on product pages. It does on home pages | 3 |  |  | https://prnt.sc/ALYdF0Brbp_c https://prnt.sc/leZ3qQ34MbzA
35 | Front End | Recently Viewed not working in french | 3 | Done |  | https://prnt.sc/6U1zJXe-7jD9 https://prnt.sc/LwGTiinqs0kT
36 | Front End | if there is no variant - all none no option should be displayed on frontend and user should be able to buy it directly without selecting any option | 3 |  |  |  | Sanjeev | If there is only 1 option as onyl type/ color/ size - then user should be able to select the option and add to cart it done
37 | frontend | Show product attributes in french | [6 empty] | https://docs.google.com/spreadsheets/d/1AUQnU_AdYW2OifAoH3RFe9C1Pe-RTJFGUmrIawhLBNg/edit#gid=0
38 | backend | on order entry under client account info we need to see the check markes there for email confirmations | 3 | Done
39 | Backend | Order entry > Customer - show all details in customer view which are displayed on edit customer | 3 |  |  | https://prnt.sc/3Xjk8kl-zvbn
40 | backend | when change language or confirmation phone number glitches asks for 10 digits | 3 | Done |  |  |  |  | order entry - edit customer - showing error for phone niber even when user did not changed
41 | Backend | Order entry > Product - email confirmation - should be checked / unchecked same as saved under customer section | 3 | Done |  | https://prnt.sc/m-HA-DH5nhE9
42 | Backend | Order entry > Product - email confirmation - email dropdown should show the emails present under billing address or an option to enter the email manually | 3 |  |  | https://prnt.sc/Zn9bgbZiSOF8
| Backend | - Product listing - Increase the size of product image |  | Done |  | https://prnt.sc/UBHT1xAA8Sc2
| backend | - edit ticket - user should be able to edit the details like address or phone in same ticket window and the card message as well should be able to edit, edit the product note, order notes should be able to do that |  | Done
| backend | pdf print option - only show single option (english or french) as per user language
43 | frontend back end | all text should be same on invoice on checkout, order screen, email and pdf | 3 | [5 empty] | Frais de livraison, Delivery charge, TPS/GST (for english and french), TVQ/QST (for english and french) Order total
44 | Products | Products - if every variant is inactive then do not show the product on frontend, even if the product is Active | 4 | In-progress |  | https://prnt.sc/wZ5SVlsOmGQj https://prnt.sc/El9ELYxG8Vgw |  | We will also show an alert in edit product, if user updates all variations to inactive and then try to save by keeping product status as Active, then we will show an alert like : please make atleast 1 variation active
45 | backend | in delivery tab when an order is designed should show the green designed icon now it is black when designed | 4 | [5 empty] | change the same icon to green color | 1
46 | Backend > Products | Products > edit - need to be able to sort by the records, by type, color, option, price, status, | 4 | [6 empty] | wait
47 | backend | in order entry we should be able to override the email address taht is used and how do we poick a different one from billing address drop down | 4 | [5 empty] | should be functional with checked and unchecked by default checked | manually add thee email,
48 | Frontend | Change the position of notes in frontend, Show Addition Information in place of Special delivery Info Move Special Delivery Instructions in-between Delivery Date and card message | 4 |  |  | https://prnt.sc/W9cWQUsyX02u |  |  |  | nice to have/ wait
49 | Frontend /backend | Save credit cards | 4
50 | backend | driver center to go under delivery center, need to perhaps have all delivery driver to go under one tab and should open under new window, with own webaddress? | 4 | [5 empty] | open in new tab move Driver center under Delivery Center, like a sub menu or a new tab
51 | Backend | Order entry > Order history - need an option 'Copy Ticket' | 4 | In-progress |  | https://prnt.sc/jYuAGR-lRze3
52 | backend | in order entry and see past sales order we should be able to copy sale | 4 |  |  |  | same as above point
53 | backend | if there can be a category called sales, and if it can auto display all products that have a sale on them | 5 |  |  |  | Sayad |  |  | popular > show all products which are on sale https://prnt.sc/pAiOwHshqB22 discuss with team
54 | backend/ frontend | when in order entry the ticket photo link is no longer there | 5 | [5 empty] | order details - should be visible on frontend as well | wait
55 | backend | order total justify to right as in emails | 5 | [6 empty] | wait
57 | Frontend > Products | Frontend > Products with sold out banner - need to change size of banner - check description | 6 |  |  |  | Sayad |  |  | wait
58 | Frontend | 8- Frontend > footer - remove email, check screenshot "Show a link text as Contach Us which will redirect the user to email popup 12" | 6 |  |  | https://prnt.sc/uu9rt5UpUvCX | Sayad |  | Show a link text as Contach Us https://prnt.sc/5kEBiE6PMsl5 add google captchs to avooid spam email | 1
59 | front end | banner text message field | 6 | [5 empty] | 15 - discuss in more detail | wait
60 | Backend | Tickets > need to be able to search with employee name as well | 6 | [6 empty] | wait
61 | Backend > Ticket details | In product details, place desinger next to Name/SKU, such that Total price will be in sequence with Subtotal | 6 |  |  | https://prnt.sc/goNB5uzlFlDi |  |  | https://prnt.sc/8qQwIyBsjYjp | 1
62 | Products | Products - Add existing variation- need to be able to choose/ search with sku | 7 |  |  | https://prnt.sc/4TF7jYXUi8_H | Sanjeev |  |  | wait
63 | Products | Products - deleting a product, should ask if you want to delete all variants | 7 |  |  |  | Sanjeev |  |  | wait
64 | Frontend > Favorites | Frontend > feature to add - My account > Favorites - to mark products as favorite - add heart shapped icon with products to add | 7 |  |  | https://prnt.sc/6IBAXpJtnsnH |  |  |  | wait
65 | Frontend > footer | Frontend > footer - need to add a link for Calculate shipping link in footer, please check screenshot | 7 |  |  | https://prnt.sc/Vuan9jlWrbCa https://prnt.sc/uxiaD2IcvCNr https://prnt.sc/H_yO8MFQuHVV |  |  |  | wait
66 | backend | designer center when mark designed and change to not designed and click search again it keeps going to all | 7 | [6 empty] | 1
67 | Backend > Products | Products > Variation popup/ edit - need an option to delete the multiple variations &same on the product edit, bulk action | 8 | [6 empty] | wait
68 | Frontend | Frontend > mega menu - need to have a price range filter | 8 |  |  | https://prnt.sc/7sdZTKI0DFEl |  |  |  | 1
69 | backend | order entry, when copy or new ticket, should add option to remove /delete ticket from drop down also | 8 | [6 empty] | remove it
70 | Backend > Ticket details | In ticket details under Customer details, place the email in bottom after phone number | 8 | Done |  | https://prnt.sc/dJFURruFXwb3
71 | backend | Products > if there is another way we can make products on sale when we want a percentage discount on all the varients of a product , if we can have a function on the top of the varients with start end date. | 9 | [6 empty] | discuss team product sale, %age sale category sale start and end date
72 |  | Item - need to be able to delete multiple items at once, like bulk action | 9
73 |  | Item - filter - need to be able to filter by child category, published / unpublished | 9 | [6 empty] | ok
74 | backend | Barcoders | 10 | [6 empty] | wait
75 | backend | items shared data base | 11 | [5 empty] | 15 - discuss in more detail | wait
76 | backend | designer recipe item count | 11 | [5 empty] | 15 - discuss in more detail | wait
77 | backend | stats tab under customer card, and in order entry | 11 | [5 empty] | to show average sale, number of order total sales, balance due... 15 | wait
78 | backend | quote email | 12 | [5 empty] | 15 - discuss in more detail | https://prnt.sc/IsLs7f9bifTz
79 | backend/front end | Large format greeting card | 12 | [5 empty] | 15 - discuss in more detail | wait
80 | Backend | Order entry > delivery date - show popup for holliday | 14 | [6 empty] | show popup or block the dates same as in frontend
81 | Backend/ Frontend | For the second image which changes on mouse hover, need to show the last uploaded image or add another option to upload the image | 15 | [6 empty] | wait
82 | front end | birthday reminder emails | 17 | [6 empty] | wait
83 | front end | recipeint type |  | In-progress |  |  |  | when select Bureau remove faculatife, When select Salon funéraire, box to say Nom du salon, When Funeral home should say name of Funeral Home
84 | frontend | when checking out product goes in frenchthen next step at check out switches to english
85 | frontend | option to check in with text code | [7 empty] | wait
86 | backend | when changing seo title, it saves but when you go back in it reverts to the product title |  | Done
87 | frontend | Newsletter – klavio account info should be exported to klavio as per language selected need to send marketing email, put the address book in klavio as per the language |  |  |  | https://prnt.sc/aeGhk8H-tE-A |  |  |  | - integrate email address of client into klavio - email marketing (create script for ecporting email addresses) provide a checkbox to user if they want to register on klavio (if new user is registered then user will check the checkbox for klavio)
88 | backend | the product note section should be for our internal use only. But we do have some products where the clients will need to enter text. like these. We have the place for it but its not active i believe |  |  |  | https://prnt.sc/mjOyio_nmykW |  |  | https://www.lebouquet.com/en/banner/
| Frontend/ backend | Second website | [6 empty] | at last | 1
| frontend | - Select option should be above the option, at 3rd place | [7 empty] | wait
| frontend | - Add to cart button should always appear and show message Please select one option - Doordash example |  | Done
| frontend | - Order revirew page : align subtotal add coluns in front of everyone |  | Done |  | https://prnt.sc/lIcLSHpMw-qR
| frontend | - Order review - need to show same like order summary, keep the same layout order date deleviry date, gst, pst show like the thankyou page
| frontend | - customer should see the selected card under my account > orders | [7 empty] | redirect user to ticket detail page
| backend | - need a checkbox for delivery confrimation email, user can check and uncheck from tickets window |  | Done |  | https://prnt.sc/R95hKNMFjtYA |  | check from point 15 onwards above
| backend | - should be able to change the Delivery confirmation email under Tickets
| backend | - add new variations under Order entry > browse products |  |  |  | https://prnt.sc/4vqlCVTD4HnW |  |  |  | product search on order entry
| backend | - same view for product under tickets, same like order entry, and same for checkboxes and notes |  |  |  | https://prnt.sc/pWAcgtW9qPDS |  |  |  | wait
| backend | - place both print options in design center and not the email button |  | Done
| backend | - order entry > show all records in scroll under Customer |  | Done |  | https://prnt.sc/OppcXjZwW1Mo |  | can show a Load More button, to show more records
| frontend | Mega menu should be displayed as per POS categories | [7 empty] | wait
|  | - Add Customer from Backend, the email confirmation checkboxes should be checked by default https://prnt.sc/04MboJG-nbOW | [7 empty] | review
|  | - Add Customer > selected language as French but on edit mode language is displayed as English, working fine when updated the user in edit mode | [7 empty] | review
|  | - Order Entry > Save a customer > the email confirmation checkboxes should be checked by default https://prnt.sc/_7Dahu2k3d6o | [7 empty] | review
|  | - Order Entry > add a customer from order entry and then select a product, email is not displayed and checkeboxes should be marked as saved while adding customer https://prnt.sc/i2V_HoG4A85X this is working fine, when admin search a customer and then select the customer | [7 empty] | review
2024-06-18
1 | backend Order entry | when searching custromer with more than 1 thing checked takes way too long toi find. i tried 5142389024
2 | backend Order entry | When i do find client Language does not show | - | [6 empty] | company name edit customer search with company name Business Name should appear
3 | backend Order entry | When i select name from drop down for past recipient it auto fills but province is incorrect, it sasy Alberta |  | done
4 | backend Order entry | When selecting products we do not see all the products, flow of attributes has to be same as frontend on website
5 | backend Order entry | Email confirmation and delivery confirmation boxes are not checked off even though they are on the client detail card | - | done
6 | backend Order entry | Need to be able to edit tickets both front end and backend, at least to start at least the text and addresses |  | done
7 | backend tickets | need to be able to filter multiple sections like designed and deliveries |  | wait
8 | backend tickets | When we go to print want it to simple open print page and not open it in a new browser tab, just open print function | - | wait
9 | backend delivery center | Delivery center, created route but i dont see it in raod warrior, it created the route but no addresses are there |  | done
10 | backend tickets, | under images, the emial addrerss there is incorrect, we should also be able to enter manually an email address that is not saved. and we have to be able to select the image now we cannot click the boxed |  | done
11 | backend Items | Under Items, we can only select the category, and not the child under |  | done
12 | backend Items attributes | What was this for again?? seems like missing information
13 | backend Delivery center | Can we move all tabs related to delivery under one tab? |  | wait
14
15
16
17
18
19

## Real time feedback
S. No. | Page | Description | Priority | Attachment | Dev. comment | Dev Status | Client Comments | IMAGE
| Frontend / Pickup | When using coupon, coupon amount not shown on web "thank you" web page although the amount is correct but shows on email confirmation.
| Frontend / Pickup | Special instructions not showing in web confirmation or email confirmation |  |  | Done
| Frontend / Pickup /Delivery Details | Change Select Recipient Address to: Select recipient from history address book |  |  | Done https://prnt.sc/y2Be5lpDevqx
| Frontend / Pickup /Delivery Details | Change Sélectionnez l'adresse du destinataire to: Sélectionnez un récipiendaire de votre carnet |  |  | Done https://prnt.sc/xftKW-UqSOFz
| Frontend / Pickup /Delivery Details | Correct: Type de location: Tour à condo / Appartement |  |  | Done https://prnt.sc/syu9WZQhnQXf
| back end | Filter design center by product code
| back end | Search tickets by product code and date range
| back end | Print labels for products with bar code
| back end | Able the scan orders with bar code
| back end | Sold out inventory management
| back end | Sort products by soldout status
| Delivery center back end | have grand totals at the bottom for the colums
| backend | - We need to have a better functionality to confirm new orders, if you can make it after we confirm a new weborder if it can close the tab and return to the prior page of tickets on the new web order tab. right now it takes way to long to confirm orders coming in |  |  | Done on dev
| frontend | - funeral name - show addition field as well same like office |  |  | In-progress
| backend | - funeral name - show addition field as well same like office
| frontend | - Need to translate the product name : Thankyou page and order email |  | https://prnt.sc/O3BdsgaIMZY0
| frontend | - translate in french options and variants |  | https://prnt.sc/mPZp23-Donpi
| frontend | - Cart page - no attributes are displayed in french + wrapping is also not displayed in both english and french |  | https://prnt.sc/5HkUg9lniSLz https://prnt.sc/Z81ORhjWlB6v
| frontend | - Show loader where ever it is taking time, like when user proceed to cart from checkout steps Loader should be consistant every where,
| backend | - Design center > need to add a filter by sku
| backend | - Products > Need to have filter by sold out to show sold out |  | https://prnt.sc/XKWqbGe7v_UY
| backend | - Tickets > Need option to deny order under Ticket details and show those orders under a new tab as Refused |  | https://prnt.sc/RcYrmHuVz9sZ
| frontent / backend | - gst/ pst text - Renaude will share, this needs to changed every where and in email + backend as well + every where |  | https://prnt.sc/yBm92xpsEG_g https://prnt.sc/6cJO1z2GShp5 https://prnt.sc/LVYKGOEVx-wp
| frontend | - Change the login process, user should be able to login with OTP
| frontend | - Checkout – When user has started on the checkout steps, there needs to be a timer to fill out all the checkout steps until the payment is made, as there is a case when a user has selected the delivery date before 12 PM but has finally made the payment by 1:25PM, Need to avoid such kind of situations |  | https://prnt.sc/mlgiBWX5e6OS https://prnt.sc/mvlgneV2dRKd
| front end add to cart button | i would like a price to know if we can change the add to cart button to show make 1 selection and then it changes to add to cart. Like on Doordash |  | https://www.doordash.com/store/fleuriste-fleurissimo-c%C3%B4te-saint-luc-24343852/?cursor=eyJzZWFyY2hfaXRlbV9jYXJvdXNlbF9jdXJzb3IiOnsicXVlcnkiOiIiLCJpdGVtX2lkcyI6W10sInNlYXJjaF90ZXJtIjoiIiwidmVydGljYWxfaWQiOjI4NSwidmVydGljYWxfbmFtZSI6IiJ9LCJzdG9yZV9wcmltYXJ5X3ZlcnRpY2FsX2lkcyI6WzE0NiwxNjksMjcyLDI4MywyODUsNCwyNzIsMjg1XX0=&pickup=false
| FRONT END ATTRIBUTES IN FRENCH | The buttons on the french side are still in English. Please see ATTRIBUTE NAMES tab for translation. |  | https://docs.google.com/spreadsheets/d/1SqHUW8CN5VyKj_aT1p1T3SY9NlpBGAotS_-IfE5gnd4/edit?usp=sharing
Points from Upwork
1 |  | - Change the icon of mothers Day to the funeral and redirect to the funeral link (https://lebouquet.brstdev.com/en/funeral/) of the home page |  |  | Done
2 |  | - clear the selected card message, if user changes the Occasion after selecting card message |  |  | Done
3 |  | - 400 character limit for cards |  |  | Done
4 |  | - 16 px default size for cards |  |  | Done
5 |  | - start one line lower for cards |  |  | Done
6 |  | - max 22px text size for cards |  |  | Done
7 |  | - Make the message format (in new lines start as per the message type) once we choose from the dropdown https://prnt.sc/HP1-3QvDGjDX |  |  | Done
8 |  | - Only display the visible area, the rest area will be a hideout for the content on cards |  |  | Done
9 |  | - the card width is the same as on the frontend https://prnt.sc/MCo82r08Ymj_ |  |  | Done
10 |  | - In the Ticket details page, it should show the same as when taking the order or the same like the PDF print out, |  |  | Done
11 |  | - We have implemented the dynamic emails in Ticket details under Ticket Images. |  |  | Done
12 |  | - We have placed the customer email under phone number in Ticket details page |  |  | Done
13 |  | - We have worked on displaying the child category filter under Items |  |  | Done
14 |  | - Change Send to Save |  |  | Done
15 |  | displaying the Sale banner on category page |  |  | Done
16 |  | - I created a child category under bulk flowers Bulk roses, i managed to create it in the mega menu, i move some products to it but they are not appearing in the front end |  |  | Done
17 |  | - create more categories as grandchild Under Bulk/Bulk flowers, Bulk Lisianthus, Bulk Hydrangeas, Bulk Daisies, Bulk Carantions, Bulk Gerbera, Bulk Snapdragons, Bulk Double Stock |  |  | Done
19 |  | - add more attribute to the size list : 100 Stems (100 tiges) 60 stems (60 tiges), 75 Stems (75 tiges), 200 stems (200 tiges), 225 stems (225 tiges), 250 Stems (250 tiges), |  |  | Done
20 |  | - need another attribute 300 stems (300tiges) to the size |  |  | Done
21 |  | - We have created a 'order_edit_history' table in database to save the entries against the ticket id and logged in user, when user make any edit in the ticket detail |  |  | Done
22 |  | - add attributes : 125 stems (125tiges), 150 stems (150 tiges), 175 stems (175 tiges), 275 stems(275 tiges), 350stems(350tiges) |  |  | Done
23 |  | - the notes that seem to have been entered in double. |  |  | Done
24 |  | - keep S small for all attributes |  |  | Done
25 |  | - For french, keep the first letter capital only, rest all small |  |  | Done
26 |  | - Grandchild category - need to move to live |  |  | Done
27 |  | - When user click on any parent category, it should show only the child categories first > then sub child (if any) > then products |  |  | Done
28 |  | - Will add attribute to sizes 120 stems (120 tiges) |  |  | Done
29 |  | - Image and price issue on clone functionality |  |  | Done
30 |  | - We will need to go a little deeper in some products and have great-children. under bulk gerbera we need Standard Gerbera, Mini Gerbera, Grande Gerpoms, Gerpoms. in french it is Gerbera standard, Mini Gerbera, Grande Gerpoms, Gerpoms. |  |  | Done
31 |  | - Then grand child under bulk flowers Lilies, (french=Lys), and great grandchildren Oriental lilies (french=Lys oriental), and LA Lilies (french= Lys asiatique) |  |  | Done
32 |  | - then under Bulk roses we need grandchildren Rose 40cm, Rose 50cm, Rose 60cm, Rose 70cm (same in french) |  |  | Done
33 |  | - We will need another child under Bulk called Flower Packages (french=Ensemble de fleurs) |  |  | Done
34 |  | - Category and all child categories are displayed in the POS, https://prnt.sc/XE6PliqU20IX |  |  | Done
35 |  | - We have also worked on Past history of clients in the order entry side, https://prnt.sc/Ay5Dvn4xBRnH |  |  | Done
36 |  | - We added products to the min gerbera category and on the home page we do not see the products that are under the mini gerbera category |  |  | Done
37 |  | - The Bulk Section the grand children and great grandchildren do not appear in the french mega menu |  |  | Done
38 |  | - recipient drop down, only see 4, will it scroll down to see all past addresses. |  |  | Done
39 |  | - And when we select address it still pops up alberta province |  |  | Done
40 |  | Also we are saving Meta title and descriptions in the products in french and english, and it is not saving the french |  |  | Done
41 |  | we have a product that is in the right category but it is not appearing and i cannot figure it out |  |  | Done
42 |  | working with build recipe and it does not search well with name searching for new item i created mini gerbera illois |  |  | Done
43

## Quickbook
Account Number | Account Name | Assigned Type | Type
1120 | Accts Receivable Customers | House Account | Debit
1113 | Bank Transit | Cash | Debit
1113 | Bank Transit | Credit card | Debit
4065 | Fees Income:Frais de Livraison/Deliv Income | Delivery Charge |  | Credit
2230 | Sales Tax Payable | GST |  | Credit
2250 | Sales Tax Payable Other | PST HST |  | Credit
4145 | Sales Discounts | Discount | Debit
Account Number | Account Name | Assigned Type of Product
4175 | Sales Chocolates | Miscellaneous (parent) --Chocolates (NEW) |  | Credit
4050 | Sales Plush | Miscellaneous (parent) -Plush (NEW) |  | Credit
4025 | Sales Cut/Perishables | Loose Flowers for DIY — Loose flowers Bouquet — Cut Bouquet without vase — Presentation Style bouquet — Round Bouquet — Wedding bouquet Hand-tied — Wedding Bouquet in holder (Cascading) — Wedding Bouquet in holder (made round) |  | Credit
4030 | Sales Floral Arrangements | Arrangement — Arrangement in clients vase — Arrangement in oasis — Arrangement in plastic basic rectangular dish — Arrangement in plastic basic round dish — Church pew arrangement — Garland — Papier Mache Arrangement — Vase arrangement — Wicker Basket Arrangement Funeral Arrangements — Arrangement in Large Urn plastic container 9'' x 8'' — Arrangement in smaller plastic container 7'' x 6'' — Casket spray Half — Cross — Heart — Papier Mache Arrangement 5R size small — Papier Mache Arrangement 6R size medium — Papier Mache Arrangement 7R size large — Wall Spray — Wreath Boutoniere and Corsages — Boutoniere — Corsage — Wristlet" |  | Credit
4040 | Sales Other | "Miscellaneous (parent) --Pots and Vases ---Miscellaneous items(NEW) |  | Credit
4045 | Sales Plants | "Miscellaneous (parent) -Plants |  | Credit
4200 | Sales Roses | Bouquet — Cut Bouquet Roses without Vase (NEW) Arrangement — Arrangement in clients vase (NEW) Loose Flowers for DIY — Roses Bulk (NEW) |  | Credit

## ATTRIBUTE NAMES
ENGLISH: Type / Size FRENCH: Type / Taille |  | ENGLISH: Color FRENCH: Couleur |  | ENGLISH & FRENCH: Options |  | ENGLISH: Select Option FRENCH:
English | French | English | French | English | French | English | French
Standard | Standard | 2 Tone | Bicolore | 1 piece | 1 morceau | WITH GREENERY | AVEC VERDURE
Deluxe | De luxe | Assorted | Assorti | 100 stems | 100 tiges | WITH GREENERY AND FLORAL ACCENTS | AVEC VERDURE ET ACCENTS FLORAUX
Premium | Premium | Black | Noir | 12 assorted roses | 12 roses assorties
Exquisite | Exquis | Blue | Bleu | 12 assorted roses with vase | 12 roses assorties avec vase
6 roses | 6 roses | Blue and Red | Bleu et rouge | 12 pieces (200g) | 12 morceaux (200g)
12 roses | 12 roses | Blush | Blush | 12 pieces | 12 morceaux
18 roses | 18 roses | Brown | Marron | 12 red roses | 12 roses rouges
24 roses | 24 roses | Burgundy | Bourgogne | 12 red roses with vase | 12 roses rouges avec vase
|  | Charcoal | Charbon | 12 roses | 12 roses
|  | Circus (2-Tone) | Cirque (Bicolore) | 15 pieces (250g) | 15 Pièces (250g)
|  | Cream | Crème | 150 stems | 150 tiges
|  | Dark | Foncé | 18 pieces (300g) | 18 Pièces (300g)
|  | Dazzle / Clear | Éclat / Transparent | 18 roses | 18 roses
|  | Emerald / Green | Émeraude / Vert | 18 roses with vase | 18 roses avec vase
|  | Fuchsia | Fuchsia | 2 pieces | 2 morceaux
|  | Gold | Or | 2 tone Chrysanthemum | Chrysanthème bicolore
|  | Gold Sparkle | Paillettes d'or | 200 stems | 200 tiges
|  | Green | Vert | 22 pieces (375g) | 22 morceaux (375g)
|  | Green Sparkle | Paillettes vertes | 24 roses | 24 roses
|  | Grey | Gris | 24 roses with vase | 24 roses avec vase
|  | Lavender | Lavande | 250 stems | 250 tiges
|  | Lilac | Lilas | 3 pieces | 3 morceaux
|  | Mauve | Mauve | 30 pieces (500g) | 30 morceaux (500g)
|  | Mauve and Yellow | Mauve et jaune | 300 stems | 300 tiges
|  | Mauve, Yellow, And White | Mauve, jaune et blanc | 32 pieces (500g) | 32 morceaux (500g)
|  | Milk | Lait | 350 stems | 350 tiges
|  | Mocha | Moka | 36 roses | 36 roses
|  | Orange | Orange | 4 names | 4 noms
|  | Pale | Pâle | 4 pieces | 4 morceaux
|  | Pastels | Pastels | 400 stems | 400 tiges
|  | Peach | Pêche | 45 pieces (750g) | 45 morceaux (750g)
|  | Pink | Rose | 5 names | 5 noms
|  | Pink And White | Rose et blanc | 50 pieces (800g) | 50 morceaux (800g)
|  | Purple | Violet | 50 stems | 50 tiges
|  | Purple and White | Violet et blanc | 6 names | 6 noms
|  | Rainbow | Arc-en-ciel | 60 pieces(1Kg) | 60 morceaux (1Kg)
|  | Red | Rouge | 7 names | 7 noms
|  | Red And White | Rouge et blanc | 7 pieces (125g) | 7 morceaux (125g)
|  | Red Sparkle | Paillettes rouges | 9 pieces | 9 morceaux
|  | Red, Yellow And White | Rouge, jaune et blanc | All white daisies | Marguerites blanches
|  | Red, Yellow, Orange | Rouge, jaune, orange | All yellow daisies | Marguerites jaunes
|  | Shades of Love | Nuances d'amour | As Is | Tel quel
|  | Silver | Argent | Assorted tinted Daisies | Marguerites teintées assorties
|  | Taupe | Taupe | Asters | Asters
|  | Turquoise | Turquoise | Aubergine | Aubergine
|  | Twotone | Bicolore | BOXED | EN BOÎTE
|  | Violet | Violet | Boy | Garçon
|  | White | Blanc | Caspia | Caspia
|  | Wood | Bois | Cello + AquaPick | Cello + AquaPick
|  | Yellow | Jaune | Cello + AquaPick + Green | Cello + AquaPick + Vert
|  | Yellow And White | Jaune et blanc | Cello + AquaPick + Green + BB | Cello + AquaPick + Vert + BB
|  |  |  | Charcoal Pot | Pot Charbon
|  |  |  | Creme | Crème
|  |  |  | Customized | Personnalisé
|  |  |  | Dad | Papa
|  |  |  | Dark 70% Chocolate | Chocolat noir 70%
|  |  |  | Dark African Cocoa | Cacao africain noir
|  |  |  | Dark Coffee Praline | Praliné noir café
|  |  |  | Dark Nibs | Nibs noirs
|  |  |  | Dark Orange | Orange noir
|  |  |  | Dark Raspberry | Framboise noire
|  |  |  | Deluxe | De luxe
|  |  |  | Diameter 22″ | Diamètre 22″
|  |  |  | Diameter 25″ | Diamètre 25″
|  |  |  | Diameter 26″ | Diamètre 26″
|  |  |  | Diameter 28″ | Diamètre 28″
|  |  |  | Diameter 32″ | Diamètre 32″
|  |  |  | Diameter 40″ | Diamètre 40″
|  |  |  | ECO WRAPPED | EMBALLAGE ECO
|  |  |  | English | Anglais
|  |  |  | English I Love You | Je t'aime en anglais
|  |  |  | English Infinity Design | Design Infini en anglais
|  |  |  | Espresso | Espresso
|  |  |  | French | Français
|  |  |  | French Je t’aime | Je t'aime en français
|  |  |  | Giraffe | Girafe
|  |  |  | Girl | Fille
|  |  |  | GREEN | VERT
|  |  |  | Greens Only | Seulement verts
|  |  |  | Gypsophila | Gypsophile
|  |  |  | Height 24″ | Hauteur 24″
|  |  |  | Height 30″ | Hauteur 30″
|  |  |  | Height 36″ | Hauteur 36″
|  |  |  | Height 42″ | Hauteur 42″
|  |  |  | Hypericum | Hypericum
|  |  |  | Infinity Design | Design Infini
|  |  |  | Large | Grand
|  |  |  | Light brown | Brun clair
|  |  |  | Loose | Vrac
|  |  |  | Loose + AquaPick | Vrac + AquaPick
|  |  |  | Maman | Maman
|  |  |  | Mauve Chrysanthemum | Chrysanthème mauve
|  |  |  | Medium | Moyen
|  |  |  | Milk | Lait
|  |  |  | Milk chocolate | Chocolat au lait
|  |  |  | Milk Hazelnut | Noisette au lait
|  |  |  | Milk Hazelnut Praline | Praliné noisette au lait
|  |  |  | Milk Salted Caramel | Caramel salé au lait
|  |  |  | Mixed pink shade | Nuances de rose mélangées
|  |  |  | Modern | Moderne
|  |  |  | Mom | Maman
|  |  |  | No vase | Sans vase
|  |  |  | Nonna | Nonna
|  |  |  | Nonno | Nonno
|  |  |  | Papa | Papa
|  |  |  | Photo 1 | Photo 1
|  |  |  | Photo 2 | Photo 2
|  |  |  | PINK | ROSE
|  |  |  | Pink Hyacinth | Jacinthe rose
|  |  |  | Premium | Premium
|  |  |  | Premium red | Rouge premium
|  |  |  | Premium white | Blanc premium
|  |  |  | Red & Pink | Rouge & Rose
|  |  |  | Red & white | Rouge & blanc
|  |  |  | Red Pot | Pot rouge
|  |  |  | Red with choclates | Rouge avec chocolats
|  |  |  | Red with plush | Rouge avec peluche
|  |  |  | Red, pink, & white | Rouge, rose, & blanc
|  |  |  | Regular | Régulier
|  |  |  | Reindeer | Renne
|  |  |  | Salted Almond | Amande salée
|  |  |  | Santa | Père Noël
|  |  |  | Script | Script
|  |  |  | Small | Petit
|  |  |  | Snowman | Bonhomme de neige
|  |  |  | Standard vase | Vase standard
|  |  |  | Taupe | Taupe
|  |  |  | Unicorn | Licorne
|  |  |  | Unisex | Unisexe
|  |  |  | Violet Pot | Pot violet
|  |  |  | Waxflower | Giroflée
|  |  |  | WHITE | BLANC
|  |  |  | White Mocha Pearls | Perles de moka blanc
|  |  |  | White Pot | Pot blanc
|  |  |  | With 15 piece box of Leonidas Chocolates | Avec boîte de 15 morceaux de chocolats Leonidas
|  |  |  | With 7 piece box of Leonidas Chocolates | Avec boîte de 7 morceaux de chocolats Leonidas
|  |  |  | with 7pc chocolat | Avec 7 morceaux de chocolat
|  |  |  | With banner | Avec bannière
|  |  |  | With black vase | Avec vase noir
|  |  |  | With Chocolates | Avec chocolats
|  |  |  | With filler flowers | Avec fleurs de remplissage
|  |  |  | With glass vase | Avec vase en verre
|  |  |  | With LED lights | Avec lumières LED
|  |  |  | With Love Vase | Avec vase Love
|  |  |  | With pink vase | Avec vase rose
|  |  |  | With purple vase | Avec vase violet
|  |  |  | With red vase | Avec vase rouge
|  |  |  | WITH WHITE VASE | AVEC VASE BLANC
|  |  |  | Without filler flowers | Sans fleurs de remplissage
|  |  |  | WRAPPED IN CELLOPHANE | EMBALLAGE CELLOPHANE
|  |  |  | YELLOW | JAUNE
|  |  |  | Yellow and white daisies | Marguerites jaunes et blanches
|  |  |  | Yellow, white and mauve daisies | Marguerites jaunes, blanches et mauves
|  |  |  | 1 Bunch | 1 poignée
|  |  |  | 3 Bunches | 3 poignées
|  |  |  | 5 Bunches | 5 Bottes
|  |  |  | 10 Bunches | 10 Bottes
|  |  |  | 15 Bunches | 15 Bottes
|  |  |  | 20 Bunches | 20 Bottes
|  |  |  | 150 Stems | 150 Tiges
|  |  |  | 250 Stems | 250 Tiges
|  |  |  | 50 Stems | 50 Tiges
|  |  |  | 10 Stems | 10 Tiges
|  |  |  | 20 Stems | 20 Tiges
|  |  |  | 30 Stems | 30 Tiges
|  |  |  | 40 Stems | 40 Tiges
|  |  |  | 60 Stems | 60 Tiges
|  |  |  | 80 Stems | 80 Tiges
|  |  |  | 75 Stems | 75 Tiges
|  |  |  | 90 Stems | 90 Tiges
|  |  |  | 120 Stems | 120 Tiges
|  |  |  | 4 Bunches | 4 Bottes
|  |  |  | 6 Bunches | 6 Bottes
|  |  |  | 1 Box | 1 Boîte
|  |  |  | 2 Boxes | 2 Boîtes
|  |  |  | 3 Boxes | 3 Boîtes
|  |  |  | 4 Boxes | 4 Boîtes
|  |  |  | 5 Boxes | 5 Boîtes